## Sheet1
ID | Story | Estimated Hours | Priority (1-5) | Sprint When Finished
1 | Implement frontend setup | 3 | 1 | 1
2 | Create basic backend | 3 | 1 | 1
3 | Finalize necessary attributes in tables | 1 | 1 | 1
4 | Setup basic database | 3 | 1 | 1
5 | Finalize database setup | 1 | 1 | 1
6 | Deploy and host in Docker | 5 | 1 | 1
7 | Allow a student to see their mentor | 8 | 1 | 1
8 | Project Website Draft | 5 | 1 | 1
9 | Configure Django Admin | 3 | 1 | 1
10 | Database should be populated | 1 | 2 | 1
11 | Implement Oauth login | 8 | 2 | 1
12 | Mentor can see a list of their mentees | 8 | 2 | 1
13 | Ability to update the database | 5 | 2 | 2
14 | Implement any other CRUD functionality | 5 | 2 | 2
15 | Mentee can fill out a form to track any meetings with their mentor | 8 | 3 | 2
16 | Mentee can fill out interest form before meeting | 8 | 3 | 2
17 | Ability to track a student from freshman to senior year | 3 | 3 | 2
20 | Login credentials to update DB | 1 | 4 | 2
21 | Mentor can view interest form responses | 3 | 4 | 2
23 | Mentee can schedule mentor meeting | 8 | 5 | 2
24 | Ability to send requests to change mentors | 5 | 5 | 2
18 | Finalize the UI | 3 | 3 | 3
19 | Ensure proper documentation | 10 | 3 | 3
22 | Finalize the project website | 8 | 4 | 3
25 | Add student workers as admins | 2 | 5 | 3
26 | Ensure all vulnerabilities are fixed | 5 | 5 | 3