## Sheet1
ID | Story | Estimated Hours | Priority (1-5) | Sprint When Finished
1 | Implement frontend setup | 3 | 1 | 1
2 | Create basic backend | 3 | 1 | 1
3 | Finalize necessary attributes in tables | 1 | 1 | 1 | Finished in Sprint 1
4 | Setup basic database | 3 | 1 | 1 | Finished in Sprint 2
5 | Finalize database setup | 1 | 1 | 1 | Finished in Sprint 3
6 | Deploy and host in Docker | 5 | 1 | 1 | Yet to be finished
7 | Allow a student to see their mentor | 8 | 1 | 1
8 | Project Website Draft | 5 | 1 | 1
9 | Configure Django Admin | 3 | 1 | 1
10 | Database should be populated | 1 | 2 | 1
11 | Implement Oauth login | 8 | 2 | 1
12 | Fix X-Frame/X-Content Vulnerabilities | 2 | 2 | 2
13 | Host website on cloud | 20 | 2 | 2
14 | Mentor can see a list of their mentees | 8 | 2 | 2
15 | Add mentor view (use roles) | 8 | 2 | 2
16 | Detect mentor vs mentee on login | 3 | 3 | 2
17 | Mentee can fill out interest form for meeting (now meeting form) | 8 | 2 | 2
18 | Mentor can view meeting log responses | 3 | 3 | 2
19 | Mentor can update meeting log with notes of their own | 5 | 3 | 2
20 | Ability to upload a csv file to populate database | 10 | 3 | 2
21 | only certain people should be allowed to access certain pages | 5 | 3 | 2
22 | Ability to send requests to change mentors | 5 | 4 | 2
23 | Meeting log should prefill with student data | 2 | 4 | 2
24 | Ability to update the database | 5 | 4 | 2
25 | Implement login attempts | 10 | 3 | 3
26 | Automate Hosting Process | 8 | 3 | 3
27 | Look into database bugs | 3 | 3 | 3
28 | Deploy to Dr. Anderson's server | 3 | 3 | 3
29 | User logged in as student can see mentor pages (bug fix) | 3 | 3 | 3
30 | Put new admin creds in env variable | 1 | 4 | 3
31 | Discuss merging mentorships table into student as attribute | 1 | 4 | 3
32 | Confirmation before changing mentors | 2 | 4 | 3
33 | Mentor profile page | 3 | 4 | 3
34 | add mc summary to meeting log modal | 1 | 3 | 3
35 | Input limits on new input fields (profiles) | 1 | 3 | 3
36 | Change student profile to look like mentor profile | 2 | 4 | 3
37 | Login credentials to update DB | 1 | 4 | 3
38 | Finalize the UI | 3 | 3 | 3
39 | Ensure proper documentation | 10 | 3 | 3
40 | Implement any other CRUD functionality | 2 | 5 | 3
41 | Finalize the project website | 8 | 4 | 3
42 | Ensure all vulnerabilities are fixed | 5 | 5 | 3
43 | Add student workers as admins | 2 | 5 | Not completed
44 | Batch updates to student attributes/mentor assignments | 8 | 5 | Not completed
45 | Add cohorts to student table | 2 | 5 | Not completed
46 | Fix verify=false certification issue | 5 | 5 | Not completed
47 | Add automated testing | 10 | 5 | Not completed